## Sponsor Feedback
PSS 9999: Sponsor name - B. Johnson, A. Ramirez
Date: 10/10/2010
Total Number of Participants: 2
Participants Responses:
On a scale of 1 - 5 how would you rate our team on the following? - (1=Poor, 2=Needs Improvement, 3=Ok, 4=Very Good and 5=Exceptional) | Rating:
Communication | 4
Management of Project | 5
Meeting your expectations | 4
Responsiveness | 5
Support from our team | 4
Overall: | 4.4
Comments:
Project went well and always knew what was going on with the project.
Team investment in the project had ups and downs, as we lost and gained team members
There were several sidebar conversations held outside of the team meetings, that changed some of the communication outcomes of the project & the PM should be included in those going forward.

## Team Feedback
PSS 9999: Sponsor name - B. Johnson, A. Ramirez
Date: 10/10/2010
Total Number of Participants: 30
Participants Responses: 30
On a scale of 1 - 5 how would you rate our team on the following? - (1=Poor, 2=Needs Improvement, 3=Ok, 4=Very Good and 5=Exceptional) | Rating:
Communication | 4
Management of Project | 5
Meeting your expectations | 4
Responsiveness | 5
Support from our team | 4
Overall: | 4.4
Comments:
Team was not fully committed to the project, which may have slowed us down a little through out the project cycle.
Losing key resources during the middle of the project, impacted our timeline and we could have asked to hire consultants to bridge the gap.