## Excel Project Template
ID | Active | Task Mode | Name of Project | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | Medium Sample Project | 65 days | 2015-04-01 | 2015-06-24 |  | 0 | 3 departments, 7 people, 1-2 days per week managing the project
1 | Yes | Auto Scheduled | Origination / Meet with Sponsor | 1 day | 2015-04-01 | 2015-04-01 |  | 1
2 | Yes | Auto Scheduled | Identify project expectations | 1 day | 2015-04-01 | 2015-04-01 |  | 2 | May include: scope, general timeline, resources, commitments, dependencies, budget, vendor, and any risks
3 | Yes | Auto Scheduled | Initiation | 6 days | 2015-04-02 | 2015-04-09 | 2 | 1 | May also include: contracts, risk draft etc.
4 | Yes | Auto Scheduled | Enter Project into PSS / Create PSS # | 1 day | 2015-04-02 | 2015-04-02 | 2 | 2
5 | Yes | Auto Scheduled | Conduct Kick off meeting | 1 day | 2015-04-03 | 2015-04-03 | 2 | 2
6 | Yes | Auto Scheduled | Define Team Roles and Res | 1 day | 2015-04-03 | 2015-04-03 | 4 | 3
7 | Yes | Auto Scheduled | Create Project Definition Document | 2 days | 2015-04-06 | 2015-04-07 | 6 | 2 | Confirm Project Success Factors
8 | Yes | Auto Scheduled | Finalize Project Definition Document | 1 day | 2015-04-08 | 2015-04-08 | 7 | 2
9 | Yes | Auto Scheduled | Sponsor's Approval to Proceed | 1 day | 2015-04-09 | 2015-04-09 | 8 | 2 | Finalize Project Success Factors
10 | Yes | Auto Scheduled | Planning | 25 days | 2015-04-10 | 2015-05-13 | 9 | 1
11 | Yes | Auto Scheduled | Gather Requirements | 5 days | 2015-04-10 | 2015-04-16 | 9 | 2
12 | Yes | Auto Scheduled | Obtain Department Lead Requirements | 5 days | 2015-04-10 | 2015-04-16 | 9 | 3
13 | Yes | Auto Scheduled | Create Communication Plan | 2 days | 2015-04-17 | 2015-04-20 | 12 | 2 | Review with team prior to finalizing. Give 3 days for the team to provide feedback via email on in a team mtg.
14 | Yes | Auto Scheduled | Create Project Schedule | 2 days | 2015-04-21 | 2015-04-22 | 13 | 2 | May also include: timeline, milestones, work break down structure (WBS), budget, and vendors
15 | Yes | Auto Scheduled | Define Approach in Managing Issues and Risks | 1 day | 2015-04-23 | 2015-04-23 | 14 | 2
16 | Yes | Auto Scheduled | Create Resource Plan | 1 day | 2015-04-24 | 2015-04-24 | 15 | 2
17 | Yes | Auto Scheduled | Create Testing Approach and Plan | 1 day | 2015-04-27 | 2015-04-27 | 16 | 2
18 | Yes | Auto Scheduled | Identify Training Approach | 2 days | 2015-04-28 | 2015-04-29 | 17 | 2
19 | Yes | Auto Scheduled | Finalize Requirements | 2 days | 2015-04-30 | 2015-05-01 | 18 | 2
20 | Yes | Auto Scheduled | Confirm Department Lead Final Requirements | 2 days | 2015-04-30 | 2015-05-01 | 18 | 3
21 | Yes | Auto Scheduled | Finalize Communication Plan | 2 days | 2015-05-04 | 2015-05-05 | 20 | 2 | Could be a 1 day review and complete or two day for additional items to consider.
22 | Yes | Auto Scheduled | Finalize Approach in Managing Issues and Risks | 2 days | 2015-05-06 | 2015-05-07 | 21 | 2 | May also include: contingency planning
23 | Yes | Auto Scheduled | Finalize Schedule with Team | 2 days | 2015-05-11 | 2015-05-12 | 22 | 2 | May also include: vendors, stakeholders, sponsor and any other team member critical to the project success
24 | Yes | Auto Scheduled | Finalize Resource Plan | 1 day | 2015-05-13 | 2015-05-13 | 23 | 2
25 | Yes | Auto Scheduled | Execution | 27 days | 2015-05-14 | 2015-06-18 | 24 | 1
26 | Yes | Auto Scheduled | Development | 7 days | 2015-05-14 | 2015-05-22 | 24 | 2
27 | Yes | Auto Scheduled | Testing | 5 days | 2015-05-25 | 2015-05-29 | 26 | 2
28 | Yes | Auto Scheduled | Manage Issues and Update Risks | 2 days | 2015-06-01 | 2015-06-02 | 27 | 2 | Hold Team Status Meetings and Create Status Reports
29 | Yes | Auto Scheduled | Manage Changes in Scope | 5 days | 2015-06-03 | 2015-06-09 | 28 | 2
30 | Yes | Auto Scheduled | Execute Communication Plan | 2 days | 2015-06-10 | 2015-06-11 | 29 | 2
31 | Yes | Auto Scheduled | Training | 2 days | 2015-06-12 | 2015-06-15 | 18,30 | 2
32 | Yes | Auto Scheduled | Obtain Sponsor's Approval to "Go-Live" | 2 days | 2015-06-16 | 2015-06-17 | 31 | 2 | May also include: executing the contingency plan
33 | Yes | Auto Scheduled | Complete Go live | 1 day | 2015-06-18 | 2015-06-18 | 32 | 2 | Implementation successful, minimal action items or follow-up's for the team post-implementation
34 | Yes | Auto Scheduled | Closeout | 4 days | 2015-06-19 | 2015-06-24 | 33 | 1
35 | Yes | Auto Scheduled | Confirm Critical Success Factors | 1 day | 2015-06-19 | 2015-06-19 | 33 | 2
36 | Yes | Auto Scheduled | Confirm Requirements and Deliverables have been completed | 1 day | 2015-06-22 | 2015-06-22 | 35 | 2
37 | Yes | Auto Scheduled | Hold Close-out meeting | 1 day | 2015-06-23 | 2015-06-23 | 36 | 2 | Includes Lessons Learned (3 things that went well, 3 things that can be improved upon per team member)
38 | Yes | Auto Scheduled | Update PSS and archive project folder | 1 day | 2015-06-24 | 2015-06-24 | 37 | 2